ANNEX II: TERMS OF REFERENCE

# BACKGROUND INFORMATION

## Partner country

North Macedonia

## Contracting authority

Roma Entrepreneurship Development Initiative- REDI Skopje

## Country background

According to EC surveys and studies11 12, the Roma population represents the largest minority in Europe (c. 12 million Roma population), being victims of discrimination and social exclusion, with one in three being unemployed and 90% are living below the poverty line.

DG NEAR has invested heavily in the Western Balkans and Turkey, promoting Roma integration and empowerment in the past period, while supporting projects bridging education and skills required by the job market. But Roma job seekers, even with degrees, are routinely turned down when applying for jobs positions. Several organizations support advocacy and litigation challenging this. At the same time and building on the belief that community development and entrepreneurship are directly connected, this proposal seeks to empower and build the capacity of Roma to create jobs for themselves—as well as jobs and social benefits for the wider Roma community.

The project “Advancing Roma Entrepreneurship in Western Balkans” is implemented in North Macedonia and Serbia because, in these countries, there is a large number of Roma entrepreneurs with the potential to grow and develop their businesses. REDI has a good presence in both countries and has established offices with field teams and resources. REDI have also developed and implemented programs in both countries in the last four years, aiming to create an ecosystem of economic development of Roma communities. Additionally, REDI is well known, recognized and positioned in both countries, having established good cooperation with state institutions and Roma community movements such as Avaja (North Macedonia) and Opre Roma (Serbia), that support our advocacy efforts and targets on employment and entrepreneurship of Roma.

REDI’s long term vision is to build an entrepreneurial ecosystem in Roma communities, which requires us to develop from scratch many critical components such as access to information about grant opportunities and contracts, a network of consultants and knowledge providers to help solve administrative issues related to business formalization, access to a network of mentoring and support, business development and business facilitators and access to finances to enable Roma entrepreneurs to grow their businesses and become agents of change.

## Current situation in the sector

Since 2007 the European Commission, the Council of Europe Development Bank (CEB) and other public social investors have embraced the concept of economic empowerment of vulnerable communities. Access to finance was identified as one of the critical areas needed in order to promote growth in vulnerable communities with several investment tools being launched in the so-called “Progress Microfinance.”

In 2009, the European Commission launched the Western Balkans Investment Framework (WBIF), which, since the end of 2019, includes the Western Balkans Enterprise Development and Innovation Facility (WB EDIF) to support the private sector in the Western Balkans region. As part of WB EDIF, the European Commission, in partnership with the European Investment Bank, the European Investment Fund, and the European Bank for Regional Development, has launched several financial instruments and capacity building assistance to support the development of micro-small and medium enterprises including in support of vulnerable communities. These instruments include financial guarantees, debt and equity instruments and are greatly focusing on micro, small and medium enterprises in the Western Balkans regions. To date, the Facility has not specifically addressed Roma communities.

The COVID 19 pandemic has dramatically hit Western Balkans economies. The European Commission has set up a substantial financial package to support the recovery of the economies. Currently, Roma interests are not well represented in these initiatives. Additionally, there is no other organization with the ability to attract and disburse funds to Roma entrepreneurs’ communities from the instruments made available in the region by the European Commission. Pilots have been run to determine how one could improve access to finance in disadvantaged communities. So far, programs designed to work on vulnerable groups tried different models with modest results. Based on the projects and fieldwork developed by REDI in the last three years, we can conclude that:

1. Lending and loan guarantee support alone does not work.

2. Capacity support alone is not effective, either.

## Related programmes and other donor activities

REDI is implementing the following key programmes in North Macedonia and Serbia aiming to advance Roma entrepreneurship and create an economic development in the Roma communities:

- Roma Digital Boost Program- the main goal is to develop entrepreneurial capacities of 100 Roma owned businesses from Serbia and North Macedonia thorough individual mentoring/coaching, to transit from traditional businesses to digital businesses.

- REDI Call Centre- acts as an info centre line to share information about funding opportunities by financial and public institutions, active labour measures, consultancy etc.

- Roma Business Clubs- the main goal is to empower Roma entrepreneurs to become agents of changes in promoting and shaping the economic development in their communities.

- REDI Technical Assistance and Access to finance: is a program that provides direct support to unemployed Roma and Roma entrepreneurs in applying to various funds and programs, developing business plans, consultancy, one-to-one mentoring etc.

- Roma Loan Officers Internship Program- is a 6 months internship program hosted by the financial and micro financial institutions. The program trains young Roma to become Loan officers.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

To advance employment and the economic situation of Roma in Serbia and North Macedonia. In order to do this, we aim to focus on:

- building human capacity to work both with entrepreneurs on the field and with financial institutions,

- piloting new mechanisms for business development and access to finance,

- set-up networks of entrepreneurs to provide peer learning opportunities,

- launch advocacy campaigns challenging the government to improve their services for Roma communities,

- establish partnerships with relevant stakeholders

The objective of the assignment is to facilitate a transition of 100 Roma businesses from traditional to digital business model through Roma Digital Boost accelerator program and to work on the grow of their businesses.

In the table you can see the draft program of the RDB 2023-24:

| Roma Digital Boost 2023 |  |  |
| --- | --- | --- |
| Goal: develop entrepreneurial capacities of 100 Roma owned businesses from Serbia and North Macedonia thorough developed workshops and individual mentoring/coaching, to transit from traditional businesses to digital businesses. |  |  |
| Objectives: O1. To enable 100 Roma owned businesses in Serbia and North Macedonia to transfer their traditional businesses to the digital sphere by providing them individual mentoring, training and workshops on digital marketing, e-commerce, financial management, legal and regulatory requirements. O2. To create a sustainable and scalable model that can be replicated in other regions and countries to support the digital inclusion of Roma entrepreneurs. O3. To build a network of Roma entrepreneurs, mentors, and trainers to support the continued development of Roma-owned businesses. |  |  |
| Activity | Description | Methodology |
| Pre-program assessment | Needs assessment questionnaire (50 questions) | individual meetings with participants to collect the information and data |
| Workshop 1: Digital Marketing | one day workshop on digital marketing strategy for a business, including branding, content creation, and analytics. | Presentation + group work + individual assignment |
| Individual Mentoring- Digital Marketing (3 individual sessions) | 120 min/ per individual session session 1: product photography session 2: content session 3: online promotion and sale | one to one mentoring + assignment+ evaluation of the module |
| Workshop 2: Legal and regulatory framework | one day workshop on overviewing the legal and regulatory requirements for conducting a traditional business and online business, including data privacy, intellectual property, and consumer protection. Training on how to comply with legal and regulatory requirements, including creating a privacy policy, terms of use, and refund policies. | Presentation + group work + individual assignment |
| Individual Mentoring- Legal and regulatory framework (1 session) | 120 min/ per individual session determining the steps for the transition to a formal business or digital business | one to one mentoring + assignment + evaluation of the module |
| Workshop 3: Financial Management | one day workshop on overview of financial management tools and techniques for businesses, including bookkeeping, budgeting, and financial analysis. Training on how to use financial management software and online banking tools. | Presentation + group work + individual assignment |
| Individual Mentoring- Financial Management (2 individual sessions) | 120 min/ per individual session session 1: session 2: | one to one mentoring + assignment+ evaluation of the module |
| Workshop 4: E-commerce | one day workshop on overview of e-commerce platforms and online marketplaces. Hands-on training on how to set up an online store, manage orders, and process payments. | Presentation + group work + individual assignment |
| Individual Mentoring- E-Commerce (3 individual sessions) | 120 min/ per individual session session 1: session 2: session 3: | one to one mentoring + assignment+ evaluation of the module |
| Evaluation of the program + post program evaluation | each module will be evaluated through a short questionnaire to assess the success and importance of the module. Post program evaluation will be conducted after the completion of the program to measure the impact of the program on participants' digital literacy, business practices, and outcomes. | Evaluation form |
| Follow up mentoring and support from REDI BF- (12 months) | after the completion of the program participants will be able to receive a mentorship support from the REDI field team in the period of 12 months | one to one mentoring + assignment+ evaluation of the follow up mentorship |
| Follow up evaluation of the program | conducted six months after the program's completion to measure the sustainability and longer-term impact of the program. | Evaluation form + indicators |

## Purpose

The purpose of the consultancy is to provide actual assistance in form of individual mentorship and coaching to support at least 50 entrepreneurs in their business development (services on digitalization, formalization, technical assistance, networking). The mentorship and coaching should be provided through at least two individual mentoring sessions by the contracted experts and REDI staff. During the mentorship and coaching, the experts will assess the needs of every entrepreneur and his/her business and work on their improvement. The assistance should also include transfer of knowledge on product photography and brand identity to the entrepreneurs.

## Results to be achieved by the contractor

During the course of the assignment, the consultant(s) is expected to produce the following results:

- Needs assessment of the entrepreneurs, end of August 2023,

- Work plan for each individual mentoring session, end of August 2023,

- Schedule for the mentoring and coaching process of the entrepreneurs, beginning of September 2023,

- Report on the mentoring and coaching process, up to one week after finishing the session,

- Folder dossier for each business facilitator with individual feedback, by end of December 2023,

- Folder dossier for each entrepreneur with individual feedback, by end of December 2023,

- Full assignment report, by end of January 2024.

It should be noted that all the deliverables are subject to approval by the REDI team.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- We estimate that Roma entrepreneurs will be opened to offer information to the consultants about their business needs.

- The Consultant delivers on time the mentorship needs assessment and schedule.

- REDI field team dedicates enough time to support the consultants during the process.

- The mentoring sessions are implemented as schedule.

## Risks

Not Applicable. Work must be provided in the general context of COVID 19 Pandemic.

# SCOPE OF THE WORK

## General

### Description of the assignment

The objective of the assignment is to facilitate a transition of 100 Roma businesses from traditional to digital business model through Roma Digital Boost accelerator program and to work on the grow of their businesses.

The purpose of the consultancy is to provide actual assistance in form of individual mentorship and coaching to support at least 50 entrepreneurs in their business development (services on digitalization, formalization, technical assistance, networking). The mentorship and coaching should be provided through at least two individual mentoring sessions by the contracted experts and REDI staff. During the mentorship and coaching, the experts will assess the needs of every entrepreneur and his/her business and work on their improvement. The assistance should also include transfer of knowledge on product photography and brand identity to the entrepreneurs.

The assistance is expected to offer the participants individual mentorship and coaching to support their business development (services on digitalization, formalization, technical assistance, networking). The mentorship and coaching should be provided for at least two rounds of individual mentorship session. The mentorship and coaching process should be performed in the period between the months of September 2023 and December 2023.

The consultant’s output is expected to include:

- Needs assessment of the businesses,

- Work plan for each individual mentoring session,

- Report on each mentoring and coaching session,

- Individual folder dossier with all products/documents (product photography, pictures, logo, links, etc) from the mentoring process for each entrepreneur,

- Full assignment report.

### Geographical area to be covered

North Macedonia and Serbia

### Target groups

Description of the target Group:

- Existing female and male Roma entrepreneurs (18 - 70 years old) with a formal or informal business in Serbia and North Macedonia (and potentially in Albania, Montenegro and Kosovo).

- Prospective female and male Roma entrepreneurs (18 - 70 years old) considering setting up a business

- Roma communities identified and mapped in projects developed by REDI previously in Serbia and North Macedonia

## Specific work

# The Consultant has the following tasks and responsibilities:

- Preparing, organizing and delivering the mentoring and coaching,

- Developing social media content (brand identity and product photography),

- Providing mentorship support to each entrepreneur in the field of digital marketing including: social media presence, product photography, content creation, online promotion and sales,

- Providing mentorship support to each entrepreneur in the field of legal business regulations in the implementing countries,

- Providing mentorship support to each entrepreneur in the field of financial management considering the basic knowledge to financially manage a registered and non-registered business.

- Providing mentorship support to each entrepreneur in the field of e-commerce.

- Cooperating with REDI Roma business facilitators and following their development,

- Reporting the working hours in time sheets,

- Preparing the documentation required.

## Project management

### Responsible body

Contracting Authority: REDI Skopje

Responsible for managing the contract:

Nadire Redjepi - Legal Representative, email: nadire@redi-ngo.eu

### Management structure

- The project is implemented under the agreement of 3 affiliated partners REDI Romania, REDI Skopje and REDI Serbia

- Project Manager (PM) and Project Assistant (PA): The technical requirements, project management, and its implementation will be ensured by the team of two employees in REDI Skopje (Project Manager and Project Assistant) assigned to the project that will follow the smooth implementation and will keep informed all affiliated partners of the project. All contracting details will be approved by the PM and all documentation and published work will be collected by the PA.

- Regional Officer: The Project uses a Regional Officer to ensure cross border project activities and general project implementation.

- Financial Project Officer: Will manage all financial and budgeting requirements, along with contracting details, payments and collection of supporting documents

- Roma Business Facilitators: responsible to work directly with Roma entrepreneurs and provide business development services, networking, mentoring etc. in accordance to the needs of the entrepreneurs.

### Facilities to be provided by the contracting authority and/or other parties

- To ensure good quality results, REDI will provide regional support through its Regional Officer.

- As we expect the consultancy to cover real life situations and needs, REDI will offer the support of local field officers (business Facilitators from Serbia and N. Macedonia).

- Previous studies and methodology developed by REDI.

- REDI will ensure access to all General Conditions and project implementation details that are related to the consultancy.

- Details concerning the expected results will be provided in due time and REDI will communicate all expectations on the consultancy and will provide input on the presented drafts.

- If needed, access to REDI office and facilities of REDI Skopje and REDI Serbia

# LOGISTICS AND TIMING

## Location

The operational base concerning the contract will be in Skopje, N. Macedonia.

## Start date & period of implementation of tasks

The intended start date is 14.08.2023 and the period of implementation of the contract will be 4 months from this date (work is expected to last at until the end of year 2023). In this period the contractor shall provide the mentorship and other professional support which will be expressed in consultancy hours. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Qualifications

| Education: | Advanced degree in business, marketing, economics or other areas directly related to the subject of work. |
| --- | --- |
| Experience: | Minimum of 7 years of relevant experience in the following fields: Digital marketing, Legal regulations, Financial management, E-commerce. Proven record of theoretical knowledge, practical experience and expertise in support to entrepreneurs, digital business and other related fields; Proven record of practical work with entrepreneurs; Previous experience in working in the respective economy and in-depth knowledge of the economy and the topic of the consultancy for which the consultant applies is essential; Proven training and mentoring capacities; Proven ability to provide instructions during the work process; Experience in working on and with policies and data for vulnerable groups, notably Roma, particularly in the area of employment; Proven communication, monitoring and reporting skills and ability to work in an environment requiring liaison and collaboration with diverse actors; Proven writing abilities, argumentation and negotiation skills. |
| Language requirements: | Fluency in English, as the official language of REDI. Fluency in one of the languages of the participating economies. Knowledge of Romani will be considered an advantage. |
| Other: | Familiar with MS Office applications. |

Core Values

- Demonstrates integrity and fairness by modelling REDI values and ethical standards;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability.

Core Competencies

- Demonstrates professional competence to meet responsibilities and post requirements and is conscientious and efficient in meeting commitments, observing deadlines and achieving results;

- Result-oriented; plans and produces quality results to meet the set goals, generates innovative and practical solutions to challenging situations;

- Communication: Excellent communication skills, including the ability to convey complex concepts and recommendations clearly;

- Team work: Ability to interact, establish and maintain effective working relations in a culturally diverse team;

- Ability to establish and maintain productive partnerships with regional and national partners and stakeholders, understand different concepts and approaches, assess risks and challenges and extract and articulate various ideas, ability for negotiations and reconciliation – consensus building ability;

- Ability and integrity to perform the tasks impartially and objectively, without any conflict of interests (subject to written declaration during the contracting procedure).

### Other experts, support staff & backstopping

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular, it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

The contractor will use its own equipment, facilities and means to ensure contract objectives.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and one digital copy.

- Inception Report of maximum 5 pages to be produced after three weeks from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel.

- NO interim report is needed.

- Draft final report of maximum 30 pages (main text, excluding annexes), in the format chosen by the contractor. This report shall be submitted no later than 2 weeks before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 5 days after receipt of comments on the draft final report.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The Consultant(s) should ensure an internal quality control during the implementing and reporting phase of the assignment. The quality control should ensure that the deliverables comply with the agreed requirements and meet adequate quality standards. The content of the deliverables should reflect the views of the stakeholders and is owned by them. The support of the Roma Integration project must be recognized in the deliverables, and the support of the consultant(s) may also be recognized.

## Special requirements

Contact with REDI field workers