ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVES & EXPECTED OUTPUTS	4

2.1.	Overall objective	4

2.2.	Specific Objective(s)	8

2.3.	Expected outputs to be achieved by the contractor	8

3.	ASSUMPTIONS & RISKS	9

3.1.	Assumptions underlying the project	9

3.2.	Risks	9

4.	SCOPE OF THE WORK	10

4.1.	General	10

4.2.	Specific work	10

4.3.	Project management	10

5.	LOGISTICS AND TIMING	11

5.1.	Location	11

5.2.	Start date & period of implementation of tasks	11

6.	REQUIREMENTS	11

6.1.	Staff	11

6.2.	Office accommodation	11

6.3.	Facilities to be provided by the contractor	11

6.4.	Equipment	11

7.	REPORTS	12

7.1.	Reporting requirements	12

7.2.	Submission and approval of reports	12

8.	MONITORING AND EVALUATION	12

8.1.	Definition of indicators	12

8.2.	Special requirements	12

# BACKGROUND INFORMATION

## Partner country

Turkiye

## Contracting authority

Roma Entrepreneurship Development Initiative REDI Turkiye (Roman Girişimciliğini Geliştirme İnisiyatifi Derneği)

## Country background

Türkiye, as a non-EU country in the midst of economic transformation, continues to face notable structural disparities, particularly impacting marginalized groups such as the Roma population. Despite national progress in development, Roma communities remain significantly disadvantaged in terms of access to employment, financial services, and economic inclusion.

Roma individuals in Türkiye often express a strong willingness to participate in the labor market. However, they are frequently excluded from mainstream employment programs and vocational training opportunities. Even when Roma candidates meet job qualifications, systemic discrimination, social stigma, and the absence of inclusive support mechanisms prevent them from securing and maintaining stable employment. Informality, lack of job security, and underemployment remain widespread among Roma workers.

A significant portion of Roma-owned businesses operate informally and remain outside the reach of formal financial institutions. These businesses typically lack the credit history, documentation, or financial literacy needed to access loans, grants, or investment opportunities. As a result, many Roma entrepreneurs face a cycle of low-income generation and limited prospects for growth.

Financial exclusion is further exacerbated by inadequate outreach from mainstream support systems and limited awareness of available resources. Traditional financial products and services often fail to accommodate the specific needs and contexts of Roma business owners.

Experience from past development initiatives demonstrates that providing capital or financial guarantees alone is insufficient to enable long-term economic empowerment. Roma entrepreneurs require a holistic and sustained approach that includes not only access to finance but also tailored technical assistance, mentoring, legal support, and market integration strategies.

Furthermore, advocacy efforts are essential to address structural inequalities and promote inclusive economic policies. Empowering Roma communities to actively engage in policy dialogue can help ensure that development efforts reflect their lived realities and priorities.

To achieve sustainable progress, economic inclusion strategies for the Roma population in Türkiye must be multidimensional. Addressing high unemployment, financial exclusion, and limited access to business development services requires integrated solutions that combine financial access with capacity building and systemic advocacy.

## Current situation in the sector

The Roma population in Türkiye continues to face significant challenges in achieving economic development, primarily due to structural, social, and systemic barriers that limit their participation in formal business and employment sectors.

Many Roma individuals struggle with low levels of formal education, making traditional classroom-based learning methods less effective. As a result, their business activities are often informal, family-run, and lack the scalability needed for long-term sustainability. One of the key constraints is limited access to capital, often stemming from inadequate credit history, missing documentation, and poorly prepared funding applications.

On the employment side, Roma communities face widespread discrimination, lack of access to professional networks, and frequent mismatches between their skills and labor market demands. These barriers contribute to persistent unemployment or underemployment within Roma communities.

Despite these challenges, there are emerging opportunities. Government and European Union initiatives aimed at Roma inclusion are increasing, offering new funding and support mechanisms. Additionally, the rise of the digital economy presents possibilities for Roma entrepreneurs to access broader markets through e-commerce and digital services.

Moreover, Türkiye is experiencing labor shortages in several key industries. With appropriate training and support, Roma job seekers could fill these gaps, contributing to the economy while achieving greater financial stability for themselves.

The Roma community includes a diverse range of individuals and groups, each with unique needs:

Aspiring Entrepreneurs: Individuals aiming to start or formalize businesses but who often lack registration, digital skills, and initial funding.

Informal Workers: People engaged in unregistered labor, needing legal employment pathways or support to transition into entrepreneurship.

Established Entrepreneurs: Roma business owners seeking investment readiness, access to financial tools, and strategies for growth.

Social Enterprises and Cooperatives: Roma-led cooperatives and social businesses requiring administrative support, financial assistance, and market access.

First-Time Job Seekers: Young Roma individuals in need of career guidance, skill certification, and integration into professional networks.

A significant portion of Roma entrepreneurs and job seekers find it difficult to navigate bureaucratic procedures, which hinders both business development and employment integration. Access to financial resources remains a critical challenge, limiting opportunities for business growth and stability. Training programs designed for Roma communities must be hands-on, relevant, and directly applicable to daily life in order to maintain engagement and effectiveness.

## Related programmes and other donor activities

The “EU Support to REDI Phase II: Advancing Roma Entrepreneurs in the Western Balkans and Türkiye” project aligns with the Council of Europe’s Roma Integration III initiative, creating valuable synergies that enhance the impact of both actions.

The Council of Europe’s Roma Integration III program focuses on improving socio-economic conditions for Roma communities by supporting national governments in implementing effective inclusion policies. A key component of this initiative is to advocate for measures related to employment and green and digital skills, which complements REDI’s mission to strengthen Roma entrepreneurship and financial inclusion.

The synergy between the two initiatives is in the following areas:

- Policy Alignment & Advocacy – Both programs work towards enhancing Roma access to employment and self-employment opportunities. REDI leverages insights from Roma Integration III’s policy recommendations to advocate for stronger financial inclusion policies and institutional support for Roma entrepreneurs, and contributes to the Council of Europe’s program by providing valuable insights from the field.

- Institutional Cooperation – REDI’s collaboration with government ministries, employment agencies, and financial institutions aligns with Roma Integration III’s efforts to improve public policy implementation in the Western Balkans and Türkiye. Joint participation at high level events help integrate Roma-specific business support measures into broader economic development strategies.

- Regional Impact & Knowledge Sharing – REDI and CoE Roma Integration III have opportunities to exchange best practices and research findings, particularly in areas related to Roma financial inclusion, entrepreneurship, and business networking.

By leveraging these synergies, REDI ensures that its activities complement broader Roma inclusion strategies, leading to more coordinated and sustainable economic empowerment efforts across the Western Balkans and Türkiye.

# OBJECTIVES & EXPECTED OUTPUTS

## 2.1. Overall objective

The overall objective (Impact) to which this action contributes is:

General relevance

The primary goal of the Advancing Roma Entrepreneurs in the Western Balkans and Türkiye project is to deliver comprehensive, direct support to at least 3,000 Roma entrepreneurs and unemployed individuals across the Western Balkans and Türkiye. Within the project, REDI Regional Business Centers aim to empower Roma entrepreneurs and job seekers by providing essential resources, customized mentorship support, networking opportunities, and pathways to employment.

The Regional Business Centers in Turkiye (İzmir and Edirne RBC) are designed to drive economic inclusion and empowerment for Roma communities in the Region (İzmir, Edirne and Tekirdag). Through structured business development programs, employment facilitation, and one-on-one support services, RBC provides practical, results-driven interventions that help Roma entrepreneurs and job seekers formalize businesses, secure financing, and enter stable employment. With a target of 30 entrepreneurs + 10 job seekers per month, Regional Business Center Concept focuses on incubation, acceleration, and growth programs tailored to the practical realities of the Roma community.

Objective of the Contract

The objective of this contract is to support and foster Roma entrepreneurship through programs of incubation, acceleration and growth programs. Programs will have two aspects, digitalization and business development and entrepreneurship.

The Expert for Business Digitalization plays a critical role in the initiative by integrating digital transformation strategies, e-commerce expansion, and use of e-platforms thus ensuring that Roma entrepreneurs are equipped with the skills and tools needed for the digital aspect of business.

The Expert for Entrepreneurship and Business Development plays a critical role in the initiative by integrating business planning, budgeting, business strategies, and access to finance, thus ensuring that Roma entrepreneurs are equipped with the skills and tools needed to compete in the modern economy.

The Experts will support Roma entrepreneurs coming from different stages of the business – start-ups, new businesses, as well as already established businesses that operate for more than 2 years.

### Key Responsibilities and Expected Deliverables

Business Development Programs—Incubation, Acceleration, and Growth—are designed to be experiential, mentor-driven, and hands-on. Rather than focusing on heavy theory, these programs provide practical, actionable learning that entrepreneurs can immediately apply to achieve tangible results every week.

The content of the programs has been designed as follows.

1. GROUP PROGRAMS FOR INCUBATION, ACCELERATION AND GROWTH

The following programs will be provided within the business center and will be preconditions for receiving the grants provided within the project and participating in matchmaking events.

1.1 INCUBATION PROGRAM

Available to aspiring entrepreneurs and informal businesses, this program provides foundational training in 2 modules:

1.	Entrepreneurship and Financial Literacy – Basics of business establishment, financial planning, and budgeting.

2.	Roma Digital Boost (Digital Marketing & E-Business) – Training on building an online presence and leveraging digital tools for business growth.

3.	Online KOSGEB Entrepreneurship Course – Training needs to be completed online and pass the exam in order to be able apply KOSGEB support for establishment.

Target participant per cycle: 15-20 aspiring entrepreneurs.

Duration: 2 training modules, 4 online sessions of 3 hrs. ( 3 weeks).

Prize and incentive for successful completion of the Incubation program: Participants who attend at least 75% of the program and establish a company will receive 2 individual expert sessions in the field of their choice from the offered list of experts and six months of paid accounting services.

Entrepreneurship and Roma Digital Boost programs will be certified. Additionally, completing “Online KOSGEB Entrepreneurship Course” will be facilitated in order to be eligible for KOSGEB support.

At the end of the program, there will be an in-person ceremony awarding the certificates and networking opportunity with the Roma Business Club members and participants of Acceleration and Growth programs. They will also be eligible to become members of the Roma Business Club.

1.1.1.	MODULE 1: ENTREPRENEURSHIP AND FINANCIAL LITERACY

Objective of this module: Equip participants with the foundational knowledge to start and manage a business, including financial planning, budgeting, and compliance.

Session 1: Business Fundamentals

•	Legal registration process and tax obligations.

•	Basics of business planning.

Session 2: Financial Literacy & Budgeting

•	Creating a financial plan and budget.

•	Understanding direct and indirect costs in business.

•	Managing cash flow and avoiding common financial mistakes.

Session 3: Accessing Finance and Grant Readiness

•	Available funding sources for Roma entrepreneurs

•	Understanding taxation, bookkeeping, and legal aspects

•	Based on REDI Loan navigator, suggest the best loan product.

•	Facilitate application process for access to finance.

•	Apply for self-employment grants (KOSGEB, REDI, Ministry of Trade, Ministry of Industry and Technology)

1.1.2.	MODULE 2: ROMA DIGITAL BOOST (DIGITAL MARKETING & E-BUSINESS)

Objective of this module: To help Roma entrepreneurs develop an online presence and leverage digital tools for growth.

Session 4: Digital Marketing Basics

•	Creating a strong business identity online

•	Social media marketing essentials (Facebook, Instagram, LinkedIn)

•	WhatsApp Marketing (regular updates promotions, special offers)

•	Creating an e-commerce business

•	Google Ads and Facebook Ads basics

1.2 ACCELERATION PROGRAM: SCALING STARTUPS FOR GROWTH

The Acceleration Program is designed to support early-stage businesses (up to 2 years in operations) in refining their business models, strengthening digital presence, and securing investment or financial growth. Through 3 modules, the program focuses on digital expansion, e-business strategies, and accessing finance, ensuring participants develop a sustainable and competitive business.

Target Participants: 10-15 startups.

Duration: 2 training modules, 6 sessions of 3 hrs. (over 4 weeks).

Prize and incentive for successful completion of the Acceleration program:

•	Participants who attend at least 75% of the program will receive 2 individual expert sessions in the field of their choice from the offered list of experts.

•	Will be eligible for grants application.

•	Will be eligible to apply and attend our matchmaking events in the region.

•	Will receive one on one mentorship advice on how to improve digital presence from Digital Marketing experts.

•	They will also be eligible to join the Roma Business Club.

•	Will have access to networking opportunities.

Roma Digital Boost programs will be certified. Additionally, completing “Online KOSGEB Entrepreneurship Course” will be facilitated in order to be eligible for KOSGEB support.

1.2.1. MODULE 1: HOW TO INVEST & ACCESS ADDITIONAL FINANCE AND BUSINESS STRATEGY DEVELOPMENT

Objective: Teach participants how to secure funding, attract investors, and manage finances and how to set objectives for long-term business success.

Session 1: Financial Literacy & Budgeting

•	Understanding direct and indirect costs in business.

•	Managing cash flow and avoiding common financial mistakes.

Session 2: Grant Funding & Business Loans for Startups

•	Available grants & loans for Roma entrepreneurs

•	How to write winning grant applications

•	Peer-to-peer lending and microfinance opportunities

Session 3: Scaling Your Business, Financial Sustainability & Strategic Planning

•	Long-term financial planning and investment strategies

•	Managing business risks

1.2.2. MODULE 2: ROMA DIGITAL BOOST – E-BUSINESS & E-COMMERCE ADVANCED

Objective: Equip businesses with online business capabilities, enabling them to scale operations efficiently.

Session 1: Building a Digital Brand & Social Media Marketing for Business Growth

•	Defining brand identity and value proposition

•	Leveraging Facebook, Instagram, and LinkedIn for targeted marketing

•	How to create effective ad campaigns on Google & Facebook

•	Setting up an email marketing campaign (tools & strategies)

•	Collaborating with influencers to build credibility

Session 2: Using local government e-platforms for managing business

•	What is e-certificate, e-signature and e-invoicing

•	How to use them for business purposes

•	How to access e-tax platform

Session 3: Advanced E-Business & E-Commerce for Growth (Optional)

•	Overview of e-commerce platforms

•	Building an independent e-store vs. marketplace selling

•	Handling customer complaints and feedback efficiently

1.2.3. PROGRAM CONCLUSION & NETWORKING EVENT

Recognize participant achievements and connect them with other entrepreneurs from the Roma Business Club and Incubation and Acceleration program.

✔ Certificate Awarding Ceremony.

✔ Networking with business club members.

✔ Opportunities for further funding and mentorship.

1.3. GROWTH PROGRAM

Objective: The Growth Program is designed to support established businesses (3+ years in operation) in their efforts to scale, expand to new markets, and optimize digital and financial strategies. This program provides a structured approach to business growth, helping entrepreneurs secure investment, expand operations, and enhance their digital presence while also offering customized expert guidance in critical business areas.

Target Participants: 5-10 established Roma-owned businesses members of Roma Business Club.

Duration: 3 joint training sessions + 3 individual expert sessions (6 weeks)

Completion Incentives:

•	Certificate of Completion

•	Eligibility for grants application

•	Networking opportunities

Training Modules (Joint Sessions)

Each session is interactive, with real-world case studies, Q&A discussions, and hands-on exercises where applicable.

1.3.1. SESSION 1: INVESTMENT & ACCESS TO FINANCE

Objective: Help businesses secure funding and investment opportunities to scale operations. Subjects to cover:

•	Investor expectations and how to prepare a compelling business case

•	Exploring Funding Options for Growth

•	Business loans, grants, and venture capital opportunities

•	Attracting angel investors and institutional funding

•	Peer-to-peer lending and alternative financing

•	Financial Planning & Risk Management

•	Long-term financial sustainability strategies

•	Avoiding debt traps and maintaining healthy cash flow

1.3.2. SESSION 2: BUSINESS EXPANSION & STRATEGIC PLANNING

Objective: Guide entrepreneurs in planning for long-term business growth and market expansion.

•	Entering New Markets: Local & International

•	Market research and identifying expansion opportunities

•	Legal and regulatory considerations for export and cross-border trade

•	Partnering with distributors, retailers, and wholesalers

1.3.3. SESSION 3: ADVANCED DIGITAL MARKETING & E-COMMERCE FOR GROWTH

Objective: Strengthen businesses’ digital presence and e-commerce capabilities to reach new customers and increase revenue.

•	Expanding Sales Channels Through E-Commerce

•	Selling on Amazon, eBay, Shopify, and other platforms

•	Building a direct-to-consumer (DTC) strategy

•	Payment gateway integrations and cross-border e-commerce

•	Managing online customer reviews and feedback

## Specific objective(s)

The specific objectives and outcomes  of this contract are as follows:

- Specific objective (Outcome) 1 (LOT 1):      Roma entrepreneurs enhance their digital capacity and competitiveness through tailored digitalization training and support. Improved knowledge in areas such as digital marketing, e-commerce, online branding, SEO, paid advertising, and digital customer engagement.Practical use of local e-government platforms, e-invoicing, and cross-border e-commerce tools.

- Specific objective (Outcome) 2 (LOT 2): Roma entrepreneurs gain foundational and advanced business development skills to successfully start, grow, and sustain their businesses.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- Output 1 to Outcome 1 (LOT 1): Development of curriculum for digitalization aspect of incubation, acceleration and growth programs described above.

- Output 2 to Outcome 1 (LOT 1): Delivery of digitalization training modules and reports after training delivery as per instructions above.

- Output 1 to Outcome 2 (LOT 2): Development of curriculum for entrepreneurship and business development aspect of incubation, acceleration and growth programs as described above.

- Output 2 to Outcome 2 (LOT 2): Delivery of entrepreneurship and business development training modules and reports after training delivery as per instructions above.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Roma communities are willing to engage in formal entrepreneurship and digital transformation.

- Roma entrepreneurs and job seekers are motivated to participate in training, mentorship, and formalization support if practical benefits (e.g., grants, business services) are available.

Trained experts and facilitators remain available and engaged across all stages of the program.

- Skilled personnel are retained for curriculum development, delivery, mentoring, and follow-up support.

The socio-political climate remains stable and conducive to project implementation.

- No significant changes in national or regional governance or policies that would restrict Roma participation or economic activity.

## Risks

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Low participation from Roma entrepreneurs due to distrust or lack of access | Medium | High | Strengthen outreach through Roma Business Clubs, peer-to-peer engagement, and use of Roma facilitators and mentors. |
| Digital divide and lack of infrastructure among target beneficiaries | Medium | Medium | Ensure flexible, mobile-friendly and offline materials; provide basic digital literacy sessions before advanced modules. |
| High dropout rates from training programs | Medium | Medium | Offer certification, financial incentives, and ongoing individual expert sessions to motivate consistent participation. |
| Inconsistent quality of mentoring or training delivery | Low | Medium | Apply quality control measures, develop clear curricula and deliverables, and introduce performance evaluations for experts. |

# SCOPE OF THE WORK

## General

### Description of the assignment

The Experts for Business Digitalization plays a critical role in the initiative by integrating digital transformation strategies, e-commerce expansion, and access to finance, thus ensuring that Roma entrepreneurs are equipped with the skills and tools needed to compete in the modern economy.

The Experts for Entrepreneurship and Business Development plays a critical role in the initiative by integrating business planning, budgeting, and business strategies, and access to finance, thus ensuring that Roma entrepreneurs are equipped with the skills and tools needed to compete in the modern economy.

The Experts will support Roma entrepreneurs coming from different stages of the business – start-ups, new businesses, as well as already established businesses that operate for more than 2 years.

Lot 1: The Expert for Business Digitalization

The primary objective of the Expert for Business Digitalization is to develop an online training curriculum for improving digitalization outcomes within Roma entrepreneurship, followed by the delivery of a pilot cycle of incubation, acceleration and growth program. The facilitator will provide support and guidance to Roma entrepreneurs throughout their entrepreneurial journey, from introducing digitalization to its implementation.

Lot 2: Entrepreneurship and Business Development Expert

The primary objective of the Expert for Entrepreneurship and Business Development is to develop an online training curriculum for business development and entrepreneurship followed by the delivery of a pilot cycle of incubation, acceleration and growth program.

### Geographical area to be covered

Izmir, Edirne, Tekirdag.

### Target groups

- Roma unemployed

- Roma entrepreneurs

- Roma youth

- Roma women

## Specific work

Recruited experts will be expected to develop curriculum (September 2025), and deliver a series of online / face to face sessions from August to November 2025.

## Project management

### Responsible body

Regional REDI Business Center in Izmir and Edirne will be responsible for the implementation of these activities.

### Management structure

Contracted experts will report to the Regional Business Center Coordinator.

Regional Business Center Coordinator and Business Facilitators will support the Expert in the delivery of the online and in-person sessions.

Contracted experts are expected to provide a report on the delivery of each program and feedback on engagement of the trainees. The Expert is also expected to provide feedback and recommendations for improving the program after the pilot phase.

### Facilities to be provided by the contracting authority and/or other parties

Izmir and Edirne RBCs.

# LOGISTICS AND TIMING

## Location

Experts are expected to deliver online training sessions with the potential option of delivering in person sessions in Izmir and Edirne.

## Start date & period of implementation of tasks

The intended start date is September 2025 and the period of implementation of the contract will be 5 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation. Based on development and pilot phase implementation, contracts might be extended for following cycles of implementation until the end of 2027.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

For the implementation of the above described activities we do not require key experts but experts who are contracted for a specific period and specific activities as per instructions above.

### Other experts, support staff & backstopping

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

The contracting authority could provide space in the office for the work of the experts if needed.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and one copies:

Contracted Experts are expected to provide reports on delivery of each program and feedback on engagement of the trainees. Contracted Experts are also expected to provide feedback and recommendations for improving the program after the pilot phase.

## Submission and approval of reports

The report referred to above must be submitted to the Regional Business Center Coordinator       identified in the contract. The project manager and Regional Business Center Coordinator will be      responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Output 1: Developed curriculum in business digitalization.

Indicator 1: Number of modules and sessions delivered with positive feedback from participants.

Output 2: Developed training curriculum in business development and entrepreneurship and

Indicator 2: Number of modules and sessions delivered with positive feedback from participants.

## Special requirements

- Previous experience of working with vulnerable groups (with focus on Roma population) will be considered a strong advantage.

- University degree with relevant experience.

- LOT 1 Expert: A minimum of 5 years of experience in digitalization and marketing on social media.

- LOT 2 Expert: A minimum of 5 years of experience in business development, business strategy, budgeting, and planning, business consultancy, and business growth

- Excellent communication, interpersonal, and relationship-building skills.

- Proven experience in organizing community events and workshops.

- Proficiency in Microsoft Office Suite (Word, Excel, PowerPoint) and other relevant software

- Fluency in Turkish and English is required.

- High level of empathy, cultural sensitivity, and commitment to community development.